## Gantt
Hotel Veniz Reservation System | [5 empty] | Legend:
Hotel Veniz | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Project Lead |  | Project Start Date: |  | 2019-05-06
|  | Display Week: |  | 1 |  | May | [27 empty] | June
 | time axis 2019-05-06 to 2019-06-30
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S
I. Project Overview
Project Overview | Goal | K. Estoista |  | 2019-05-13 | 1 | Week 2 M: 2
Background of the Study | Milestone | E. Naphadan | 100% | 2019-05-16 | 2 | bar: Week 2 Th to Week 2 F
Company Profile | High Risk | J. Fernandez | 100% | 2019-05-23 | 7
Objectives of the Study | Med Risk | K. Estoista | 100% | 2019-05-30 | 1
II. Methodology
Methodology | High Risk | Z. Degay | 100% | 2019-05-30 | 1
Project Planning | Goal | D. Pawid | 100% | 2019-06-17 | 4 | Week 7 M: 2; Week 7 T: 2; Week 7 W: 2; Week 7 Th: 2
Analysis | Low Risk | J. Fernandez | 100% | 2019-06-03 | 1
Design | Milestone | E. Naphadan | 100% | 2019-06-06 | 1 | bar: Week 5 Th
Implementation | Med Risk | K. Estoista | 100% | 2019-06-06 | 1
Scope and Delimitations of the Study | Med Risk | D. Pawid | 100% | 2019-06-06 | 1
Systems Analysis and Design Tools | Med Risk | Z. Degay | 100% | 2019-06-06 | 1
III. Findings of the Study
Existing Processes of the <Business Process> | On Track | Z. Degay | 100% | 2019-05-27 | 8
Problems Encountered in the Existing <Business Process> Process | Med Risk | J. Fernandez | 100% | 2019-05-27 | 4
Features of the Proposed <Business Process> System | On Track | E. Naphadan | 100% | 2019-06-17 | 4
IV. Conclusions and Recommendations
Conclusions and Recommendations |  | K. Estoista | 0%
E. Naphadan
J. Fernandez
K. Estoista
Z. Degay
D. Pawid

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.